## BOM csv data
http://www.bom.gov.au/climate/data/index.shtml?bookmark=200 | 1. CLICK THE LINK TO THE LEFT TO ACCESS THE BoM Website; 2. Select the Location and pick the nearest BoM Station;
3. Get Data (Opens in new window); 4. Download data (csv) file of statistics; 5. Open the csv file in eXcel;
6. Highlight all data (A1:end) and Copy (Ctrl C); 7. PasteSpecialValues into Cell A5 below. See notes in CLIMATE TAB re Wind data
DOWNLOAD BOM csv file & COPY+PASTE (all data) INTO CELL A5 using 'right click' :PasteSpecialValues to maintain formatting below. This data populates the Yellow 'Climate' Tab
Monthly Climate Statistics for 'MOORABBIN AIRPORT' [086077]
Created on [ 04 Apr 2018 14:44:16 GMT+00:00]
086077 MOORABBIN AIRPORT
Commenced: 1950
Last Record: 2018
Latitude: 37.98 Degrees South
Longitude: 145.10 Degrees East
Elevation: 12 m
State: VIC
Statistic Element | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Number of Years | Start Year | End Year
Mean maximum temperature (Degrees C) for years 1971 to 2018 | 25.8 | 26.1 | 23.8 | 20.2 | 17 | 14.2 | 13.7 | 14.9 | 16.9 | 19.3 | 21.7 | 24 | 19.8 | 46 | 1971 | 2018
Highest temperature (Degrees C) for years 1971 to 2018 | 44.9 | 46.7 | 40.8 | 34.9 | 26.6 | 23.7 | 23.1 | 25.6 | 31.8 | 36.2 | 39.5 | 43 | 46.7 | 46 | 1971 | 2018
Date of Highest temperature for years 1971 to 2018 | 2009-01-29 | 2009-02-07 | 2016-03-08 | 2005-04-10 | 1972-05-02 | 2005-06-08 | 2013-07-18 | 1982-08-29 | 1987-09-26 | 2006-10-12 | 2012-11-29 | 2005-12-31 | 2009-02-07 | N/A | 1971 | 2018
Lowest maximum temperature (Degrees C) for years 1971 to 2018 | 15 | 14.5 | 14.5 | 12.2 | 8.4 | 8.2 | 6.6 | 8.8 | 9.4 | 11.4 | 12.5 | 14.2 | 6.6 | 46 | 1971 | 2018
Date of Lowest maximum temperature for years 1971 to 2018 | 1996-01-02 | 1990-02-01 | 1978-03-31 | 1995-04-07 | 1977-05-31 | 1975-06-19 | 1973-07-07 | 2005-08-10 | 1995-09-05 | 1998-10-08 | 1993-11-04 | 1993-12-26 | 1973-07-07 | N/A | 1971 | 2018
Decile 1 maximum temperature (Degrees C) for years 1971 to 2018 | 19.6 | 19.9 | 18.4 | 15.9 | 13.9 | 11.8 | 11.2 | 12 | 13.3 | 14.6 | 16.2 | 18 |  | 47 | 1971 | 2018
Decile 9 maximum temperature (Degrees C) for years 1971 to 2018 | 35.3 | 34.3 | 31.5 | 25.8 | 21.2 | 16.9 | 16.3 | 18.5 | 22 | 26 | 29.8 | 32.6 |  | 47 | 1971 | 2018
Mean number of days >= 30 Degrees C for years 1971 to 2018 | 7 | 7.1 | 4.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0.8 | 2.9 | 5.1 | 27.5 | 46 | 1971 | 2018
Mean number of days >= 35 Degrees C for years 1971 to 2018 | 3.3 | 2.1 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 1.9 | 8.7 | 46 | 1971 | 2018
Mean number of days >= 40 Degrees C for years 1971 to 2018 | 0.7 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 1.2 | 46 | 1971 | 2018
Mean minimum temperature (Degrees C) for years 1971 to 2018 | 14.3 | 14.4 | 13 | 10.5 | 8.7 | 6.7 | 6.2 | 6.9 | 8.1 | 9.3 | 11.1 | 12.7 | 10.2 | 46 | 1971 | 2018
Lowest temperature (Degrees C) for years 1971 to 2018 | 6 | 5.2 | 2.9 | 1 | 0 | -2.2 | -3.8 | -2.8 | -1.8 | 0.6 | 2.2 | 1.3 | -3.8 | 46 | 1971 | 2018
Date of Lowest temperature for years 1971 to 2018 | 2009-01-03 | 1982-02-27 | 1993-03-13 | 1999-04-29 | 2008-05-24 | 1972-06-24 | 1997-07-30 | 1997-08-04 | 1997-09-29 | 1993-10-29 | 1980-11-04 | 1992-12-02 | 1997-07-30 | N/A | 1971 | 2018
Highest minimum temperature (Degrees C) for years 1971 to 2018 | 28.7 | 25.3 | 24 | 22.6 | 18.4 | 15.7 | 14.6 | 16.8 | 20.1 | 23.1 | 24.2 | 28.5 | 28.7 | 46 | 1971 | 2018
Date of Highest minimum temperature for years 1971 to 2018 | 2017-01-08 | 1981-02-09 | 2008-03-18 | 2014-04-02 | 1990-05-05 | 2002-06-07 | 1993-07-03 | 2004-08-26 | 1999-09-29 | 2017-10-19 | 1984-11-27 | 2015-12-20 | 2017-01-08 | N/A | 1971 | 2018
Decile 1 minimum temperature (Degrees C) for years 1971 to 2018 | 10.2 | 10.3 | 8.8 | 6 | 4.3 | 2.3 | 1.9 | 3 | 3.9 | 5.1 | 7.1 | 9 |  | 47 | 1971 | 2018
Decile 9 minimum temperature (Degrees C) for years 1971 to 2018 | 18.5 | 18.5 | 17.3 | 14.6 | 12.7 | 10.6 | 9.7 | 10.2 | 11.7 | 13.4 | 15.2 | 16.6 |  | 47 | 1971 | 2018
Mean number of days <= 2 Degrees C for years 1971 to 2018 | 0 | 0 | 0 | 0.2 | 0.7 | 2.6 | 3.3 | 1.7 | 0.7 | 0.1 | 0 | 0 | 9.3 | 46 | 1971 | 2018
Mean number of days <= 0 Degrees C for years 1971 to 2018 | 0 | 0 | 0 | 0 | 0 | 0.6 | 1.1 | 0.3 | 0.1 | 0 | 0 | 0 | 2.1 | 46 | 1971 | 2018
Mean daily ground minimum temperature Degrees C for years null to null
Lowest ground temperature Degrees C for years null to null
Date of Lowest ground temperature for years null to null | [13 empty] | N/A
Mean number of days ground min. temp. <= -1 Degrees C for years null to null
Mean rainfall (mm) for years 1950 to 2018 | 44.4 | 45 | 43.7 | 62.5 | 68.9 | 55.9 | 61.7 | 65.1 | 64.6 | 68.8 | 62.4 | 60.5 | 707.8 | 61 | 1950 | 2018
Highest rainfall (mm) for years 1950 to 2018 | 137 | 215.2 | 129.6 | 158.8 | 160.1 | 139.8 | 165 | 127.7 | 122.2 | 165.4 | 180.6 | 146.6 | 965.9 | 65 | 1950 | 2018
Date of Highest rainfall for years 1950 to 2018 | 1991 | 2011 | 1970 | 2001 | 1962 | 1991 | 1952 | 1975 | 1959 | 1975 | 1983 | 1954 | 1970 | N/A | 1950 | 2018
Lowest rainfall (mm) for years 1950 to 2018 | 1.2 | 0.3 | 5.4 | 8.2 | 15.2 | 5.6 | 12.4 | 12 | 24.8 | 7.4 | 5.1 | 2.9 | 443.8 | 65 | 1950 | 2018
Date of Lowest rainfall for years 1950 to 2018 | 1990 | 1956 | 1951 | 1963 | 2005 | 1994 | 1994 | 1994 | 2008 | 2006 | 1961 | 1972 | 1967 | N/A | 1950 | 2018
Decile 1 monthly rainfall (mm) for years 1950 to 2018 | 14.9 | 4.5 | 16.5 | 23.6 | 29.2 | 22.9 | 29.7 | 36.1 | 37.7 | 28.2 | 22.6 | 22.2 | 528.6 | 65 | 1950 | 2018
Decile 5 (median) monthly rainfall (mm) for years 1950 to 2018 | 38 | 33.6 | 39.8 | 62.5 | 65.4 | 55.8 | 60.6 | 64.8 | 59.6 | 66.1 | 54.6 | 57.6 | 708.9 | 65 | 1950 | 2018
Decile 9 monthly rainfall (mm) for years 1950 to 2018 | 91.7 | 89.5 | 74.4 | 107 | 108.6 | 85.1 | 94.9 | 95.4 | 99.3 | 108.4 | 110.6 | 105.4 | 884.9 | 65 | 1950 | 2018
Highest daily rainfall (mm) for years 1950 to 2018 | 91 | 140.8 | 45 | 64 | 53.2 | 51.3 | 61.5 | 42.8 | 53.3 | 72 | 61.4 | 85.6 | 140.8 | 64 | 1950 | 2018
Date of Highest daily rainfall for years 1950 to 2018 | 1998-01-13 | 2011-02-05 | 1997-03-08 | 2001-04-22 | 1974-05-15 | 1951-06-13 | 1952-07-14 | 1978-08-07 | 1959-09-20 | 2010-10-31 | 1983-11-29 | 1954-12-04 | 2011-02-05 | N/A | 1950 | 2018
Mean number of days of rain for years 1950 to 2018 | 7.9 | 6.9 | 9.1 | 11.6 | 14.8 | 14.8 | 17 | 17 | 14.6 | 13.9 | 12.2 | 10.1 | 149.9 | 65 | 1950 | 2018
Mean number of days of rain >= 1 mm for years 1950 to 2018 | 5.4 | 4.5 | 5.8 | 8.1 | 10.8 | 9.8 | 11.4 | 12.1 | 10.5 | 9.8 | 8.6 | 7.2 | 104 | 64 | 1950 | 2018
Mean number of days of rain >= 10 mm for years 1950 to 2018 | 1.4 | 1.4 | 1.4 | 1.8 | 2 | 1.5 | 1.4 | 1.7 | 1.9 | 2.1 | 2.1 | 1.9 | 20.6 | 64 | 1950 | 2018
Mean number of days of rain >= 25 mm for years 1950 to 2018 | 0.3 | 0.5 | 0.2 | 0.5 | 0.2 | 0.1 | 0.2 | 0.1 | 0.2 | 0.3 | 0.3 | 0.5 | 3.4 | 64 | 1950 | 2018
Mean daily wind run (km) for years 2002 to 2018 | 372 | 345 | 331 | 284 | 300 | 297 | 338 | 369 | 374 | 351 | 360 | 364 | 340 | 15 | 2002 | 2018
Maximum wind gust speed (km/h) for years 1972 to 2018 | 102 | 98 | 100 | 115 | 106 | 91 | 108 | 102 | 104 | 102 | 108 | 104 | 115 | 35 | 1972 | 2018
Date of Maximum wind gust speed for years 1972 to 2018 | 1974-01-03 | 1983-02-16 | 1984-03-26 | 1974-04-30 | 1977-05-20 | 1988-06-06 | 1989-07-28 | 1976-08-01 | 1982-09-03 | 2016-10-09 | 1976-11-13 | 1989-12-25 | 1974-04-30 | N/A | 1972 | 2018
Mean daily sunshine (hours) for years null to null
Mean daily solar exposure (MJ/(m*m)) for years 1990 to 2018 | 24.6 | 21.4 | 16.6 | 11.3 | 7.5 | 6.1 | 6.9 | 9.8 | 13.6 | 18.2 | 21.8 | 24.4 | 15.2 | 28 | 1990 | 2018
Mean number of clear days for years 1971 to 2010 | 1.3 | 1.8 | 1.7 | 0.8 | 1 | 0.8 | 0.9 | 0.6 | 0.9 | 1 | 0.9 | 1.2 | 12.9 | 24 | 1971 | 2010
Mean number of cloudy days for years 1971 to 2010 | 2.5 | 2.8 | 3.3 | 4.3 | 5 | 5 | 4.4 | 4.7 | 4.3 | 3.5 | 3.7 | 3.8 | 47.3 | 24 | 1971 | 2010
Mean daily evaporation (mm) for years null to null
Mean 9am temperature (Degrees C) for years 1971 to 2010 | 18.5 | 18.5 | 17.2 | 14.8 | 12 | 9.4 | 8.9 | 10.2 | 12.3 | 14.4 | 15.7 | 17.2 | 14.1 | 39 | 1971 | 2010
Mean 9am wet bulb temperature (Degrees C) for years 1971 to 2010 | 15.1 | 15.3 | 14.4 | 12.5 | 10.6 | 8.3 | 7.5 | 8.4 | 9.8 | 11.3 | 12.7 | 13.8 | 11.6 | 35 | 1971 | 2010
Mean 9am dew point temperature (Degrees C) for years 1971 to 2010 | 12.1 | 12.8 | 11.9 | 10.2 | 8.9 | 7 | 6.1 | 6.3 | 7.2 | 8.3 | 9.8 | 10.8 | 9.3 | 39 | 1971 | 2010
Mean 9am relative humidity (%) for years 1971 to 2010 | 68 | 72 | 73 | 76 | 83 | 85 | 83 | 78 | 73 | 69 | 70 | 68 | 75 | 39 | 1971 | 2010
Mean 9am cloud cover (okas) for years 1971 to 2010 | 5.3 | 4.8 | 5.3 | 5.4 | 5.7 | 5.6 | 5.6 | 5.7 | 5.5 | 5.3 | 5.6 | 5.4 | 5.4 | 25 | 1971 | 2010
Mean 9am wind speed (km/h) for years 1971 to 2010 | 15.2 | 12.7 | 13.6 | 13.3 | 13 | 13.6 | 15.6 | 17.8 | 18.8 | 18.6 | 15.9 | 16.1 | 15.4 | 38 | 1971 | 2010
Mean 3pm temperature (Degrees C) for years 1971 to 2010 | 23.2 | 24.4 | 22.2 | 18.9 | 15.9 | 13.1 | 12.5 | 13.7 | 15.3 | 17.4 | 19.4 | 21.8 | 18.2 | 39 | 1971 | 2010
Mean 3pm wet bulb temperature (Degrees C) for years 1971 to 2010 | 17 | 17.6 | 16.4 | 14.3 | 12.5 | 10.4 | 9.6 | 10.2 | 11.4 | 12.7 | 14.3 | 15.8 | 13.5 | 35 | 1971 | 2010
Mean 3pm dew point temperature (Degrees C) for years 1971 to 2010 | 12.2 | 12.4 | 11.5 | 10.1 | 9.1 | 7.5 | 6.4 | 6.2 | 7.4 | 8.3 | 9.8 | 11 | 9.3 | 39 | 1971 | 2010
Mean 3pm relative humidity (%) for years 1971 to 2010 | 53 | 51 | 54 | 59 | 65 | 70 | 67 | 62 | 61 | 58 | 57 | 54 | 59 | 39 | 1971 | 2010
Mean 3pm cloud cover (oktas) for years 1971 to 2010 | 3.6 | 4 | 4.7 | 5.2 | 5.5 | 5.7 | 5 | 5.4 | 5.5 | 5.1 | 4.7 | 5 | 5 | 24 | 1971 | 2010
Mean 3pm wind speed (km/h) for years 1971 to 2010 | 23.3 | 22 | 21.2 | 19.5 | 18.2 | 18.9 | 20.5 | 22 | 22.7 | 23 | 22.6 | 23.1 | 21.4 | 23 | 1971 | 2010

## Climate
Monthly Climate Statistics for 'MOORABBIN AIRPORT' [086077]
Statistics | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Annual |  | NOTES (scroll down)
Maximum temperature | [14 empty] | Click here to view Heat graph
Mean maximum temperature (°C) | 25.8 | 26.1 | 23.8 | 20.2 | 17 | 14.2 | 13.7 | 14.9 | 16.9 | 19.3 | 21.7 | 24 | 19.8
Highest temperature (°C) | 44.9 | 46.7 | 40.8 | 34.9 | 26.6 | 23.7 | 23.1 | 25.6 | 31.8 | 36.2 | 39.5 | 43 | 46.7
Lowest maximum temperature (°C) | 15 | 14.5 | 14.5 | 12.2 | 8.4 | 8.2 | 6.6 | 8.8 | 9.4 | 11.4 | 12.5 | 14.2 | 6.6
Decile 1 maximum temperature (°C) | 19.6 | 19.9 | 18.4 | 15.9 | 13.9 | 11.8 | 11.2 | 12 | 13.3 | 14.6 | 16.2 | 18
Decile 9 maximum temperature(°C) | 35.3 | 34.3 | 31.5 | 25.8 | 21.2 | 16.9 | 16.3 | 18.5 | 22 | 26 | 29.8 | 32.6
Mean number of days ≥ 30 °C | 7 | 7.1 | 4.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0.8 | 2.9 | 5.1 | 27.5
Mean number of days ≥ 32 °C | 5.15 | 4.6 | 2.55 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0.4 | 1.75 | 3.5 | 18.1 | <---Interpolated
Mean number of days ≥ 35 °C | 3.3 | 2.1 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 1.9 | 8.7
Mean number of days ≥ 37 °C | 2 | 1.15 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 1.05 | 4.95 | <---Interpolated
Mean number of days ≥ 40 °C | 0.7 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 1.2
Minimum temperature | [14 empty] | Click here to view Cold Graph
Mean minimum temperature (°C) | 14.3 | 14.4 | 13 | 10.5 | 8.7 | 6.7 | 6.2 | 6.9 | 8.1 | 9.3 | 11.1 | 12.7 | 10.2
Lowest temperature (°C) | 6 | 5.2 | 2.9 | 1 | 0 | -2.2 | -3.8 | -2.8 | -1.8 | 0.6 | 2.2 | 1.3 | -3.8
Highest minimum temperature (°C) | 28.7 | 25.3 | 24 | 22.6 | 18.4 | 15.7 | 14.6 | 16.8 | 20.1 | 23.1 | 24.2 | 28.5 | 28.7
Decile 1 minimum temperature (°C) | 10.2 | 10.3 | 8.8 | 6 | 4.3 | 2.3 | 1.9 | 3 | 3.9 | 5.1 | 7.1 | 9
Decile 9 minimum temperature (°C) | 18.5 | 18.5 | 17.3 | 14.6 | 12.7 | 10.6 | 9.7 | 10.2 | 11.7 | 13.4 | 15.2 | 16.6
Mean number of days ≤ 2 °C | 0 | 0 | 0 | 0.2 | 0.7 | 2.6 | 3.3 | 1.7 | 0.7 | 0.1 | 0 | 0 | 9.3
Mean number of days ≤ 0 °C | 0 | 0 | 0 | 0 | 0 | 0.6 | 1.1 | 0.3 | 0.1 | 0 | 0 | 0 | 2.1
Ground surface temperature
Mean daily ground minimum temperature (°C)
Lowest ground temperature (°C)
Mean number of days ground min. temp. ≤ -1 °C
Rainfall | [14 empty] | Click here to view Rainfall Graph
Highest rainfall (mm) | 137 | 215.2 | 129.6 | 158.8 | 160.1 | 139.8 | 165 | 127.7 | 122.2 | 165.4 | 180.6 | 146.6 | 965.9
Decile 9 rainfall (mm) | 91.7 | 89.5 | 74.4 | 107 | 108.6 | 85.1 | 94.9 | 95.4 | 99.3 | 108.4 | 110.6 | 105.4 | 884.9
Mean rainfall (mm) | 44.4 | 45 | 43.7 | 62.5 | 68.9 | 55.9 | 61.7 | 65.1 | 64.6 | 68.8 | 62.4 | 60.5 | 707.8
Decile 5 (median) rainfall (mm) | 38 | 33.6 | 39.8 | 62.5 | 65.4 | 55.8 | 60.6 | 64.8 | 59.6 | 66.1 | 54.6 | 57.6 | 708.9
Decile 1 rainfall (mm) | 14.9 | 4.5 | 16.5 | 23.6 | 29.2 | 22.9 | 29.7 | 36.1 | 37.7 | 28.2 | 22.6 | 22.2 | 528.6
Lowest rainfall (mm) | 1.2 | 0.3 | 5.4 | 8.2 | 15.2 | 5.6 | 12.4 | 12 | 24.8 | 7.4 | 5.1 | 2.9 | 443.8
Highest daily rainfall (mm) | 91 | 140.8 | 45 | 64 | 53.2 | 51.3 | 61.5 | 42.8 | 53.3 | 72 | 61.4 | 85.6 | 140.8
Mean number of days of rain | 7.9 | 6.9 | 9.1 | 11.6 | 14.8 | 14.8 | 17 | 17 | 14.6 | 13.9 | 12.2 | 10.1 | 149.9
Mean number of rain days < 1 mm | 2.5 | 2.4 | 3.3 | 3.5 | 4 | 5 | 5.6 | 4.9 | 4.1 | 4.1 | 3.6 | 2.9 | 45.9 | <---Interpolated | <-----Used in GREEN TAB <1mm
Mean number of days of rain ≥ 1 mm | 5.4 | 4.5 | 5.8 | 8.1 | 10.8 | 9.8 | 11.4 | 12.1 | 10.5 | 9.8 | 8.6 | 7.2 | 104
Mean number of rain days ≥ 1 mm and < 10 mm | 4 | 3.1 | 4.4 | 6.3 | 8.8 | 8.3 | 10 | 10.4 | 8.6 | 7.7 | 6.5 | 5.3 | 83.4 | <---Interpolated | <-----Used in GREEN TAB ≥ 1 mm & < 10 mm
Mean number of days of rain ≥ 10 mm | 1.4 | 1.4 | 1.4 | 1.8 | 2 | 1.5 | 1.4 | 1.7 | 1.9 | 2.1 | 2.1 | 1.9 | 20.6
Mean number of rain days ≥ 10 mm and < 25 mm | 1.1 | 0.9 | 1.2 | 1.3 | 1.8 | 1.4 | 1.2 | 1.6 | 1.7 | 1.8 | 1.8 | 1.4 | 17.2 | <---Interpolated | <-----Used in GREEN TAB ≥ 10 mm & < 25 mm
Mean number of days of rain ≥ 25 mm | 0.3 | 0.5 | 0.2 | 0.5 | 0.2 | 0.1 | 0.2 | 0.1 | 0.2 | 0.3 | 0.3 | 0.5 | 3.4 |  | <-----Used in GREEN TAB ≥ 25 mm
Other daily elements : Wind, Sunshine, Clear/Cloudy, Evaporation | [14 empty] | Click here to view Wind Graph
Mean daily wind run (km) | 372 | 345 | 331 | 284 | 300 | 297 | 338 | 369 | 374 | 351 | 360 | 364 | 340
Maximum wind gust speed (km/h) | 102 | 98 | 100 | 115 | 106 | 91 | 108 | 102 | 104 | 102 | 108 | 104 | 115
Mean daily sunshine (hours)
Mean daily solar exposure (MJ/m2) | 24.6 | 21.4 | 16.6 | 11.3 | 7.5 | 6.1 | 6.9 | 9.8 | 13.6 | 18.2 | 21.8 | 24.4 | 15.2
Mean number of clear days | 1.3 | 1.8 | 1.7 | 0.8 | 1 | 0.8 | 0.9 | 0.6 | 0.9 | 1 | 0.9 | 1.2 | 12.9
Mean number of cloudy days | 2.5 | 2.8 | 3.3 | 4.3 | 5 | 5 | 4.4 | 4.7 | 4.3 | 3.5 | 3.7 | 3.8 | 47.3
Mean daily evaporation (mm)
9 am conditions
Mean 9am temperature (°C) | 18.5 | 18.5 | 17.2 | 14.8 | 12 | 9.4 | 8.9 | 10.2 | 12.3 | 14.4 | 15.7 | 17.2 | 14.1 |  | Note : Some of the BoM Weather Stations
Mean 9am wet-bulb temperature (°C) | 15.1 | 15.3 | 14.4 | 12.5 | 10.6 | 8.3 | 7.5 | 8.4 | 9.8 | 11.3 | 12.7 | 13.8 | 11.6 |  | Do not have Wind Records
Mean 9am dew-point temperature (°C) | 12.1 | 12.8 | 11.9 | 10.2 | 8.9 | 7 | 6.1 | 6.3 | 7.2 | 8.3 | 9.8 | 10.8 | 9.3 |  | In this case you may need to choose
Mean 9am relative humidity (%) | 68 | 72 | 73 | 76 | 83 | 85 | 83 | 78 | 73 | 69 | 70 | 68 | 75 |  | another adjacent BoM station to download
Mean 9am cloud cover (oktas) | 5.3 | 4.8 | 5.3 | 5.4 | 5.7 | 5.6 | 5.6 | 5.7 | 5.5 | 5.3 | 5.6 | 5.4 | 5.4 |  | approximate wind data
Mean 9am wind speed (km/h) | 15.2 | 12.7 | 13.6 | 13.3 | 13 | 13.6 | 15.6 | 17.8 | 18.8 | 18.6 | 15.9 | 16.1 | 15.4
3 pm conditions
Mean 3pm temperature (°C) | 23.2 | 24.4 | 22.2 | 18.9 | 15.9 | 13.1 | 12.5 | 13.7 | 15.3 | 17.4 | 19.4 | 21.8 | 18.2
Mean 3pm wet-bulb temperature (°C) | 17 | 17.6 | 16.4 | 14.3 | 12.5 | 10.4 | 9.6 | 10.2 | 11.4 | 12.7 | 14.3 | 15.8 | 13.5
Mean 3pm dew-point temperature (°C) | 12.2 | 12.4 | 11.5 | 10.1 | 9.1 | 7.5 | 6.4 | 6.2 | 7.4 | 8.3 | 9.8 | 11 | 9.3
Mean 3pm relative humidity (%) | 53 | 51 | 54 | 59 | 65 | 70 | 67 | 62 | 61 | 58 | 57 | 54 | 59
Mean 3pm cloud cover (oktas) | 3.6 | 4 | 4.7 | 5.2 | 5.5 | 5.7 | 5 | 5.4 | 5.5 | 5.1 | 4.7 | 5 | 5
Mean 3pm wind speed (km/h) | 23.3 | 22 | 21.2 | 19.5 | 18.2 | 18.9 | 20.5 | 22 | 22.7 | 23 | 22.6 | 23.1 | 21.4 |  | These wind speeds populate the Green TAB colour scales
Calculations used in Green Tab
Heat
Editable Threshholds for HEAT Colour Scale Indicators | Low > | 19 | > Med > | 25 | >High | [9 empty] | The Thresholds for Low/Med/High ratings in the
| High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med |  |  | 4 colour scales can be edited in Columns C & E
on Rows 153, 173, 194 & 211
These ratings populate the
Red TAB rows 32:35
Cold
Editable Threshholds for COLD Colour Scale Indicators | Low < | 4 | < Med < | 2 | <High
| Low | Low | Med | High | High | High | High | High | High | High | Med | High
Rainfall Percentages
| 6.273% | 6.358% | 6.174% | 8.83% | 9.734% | 7.898% | 8.717% | 9.198% | 9.127% | 9.72% | 8.816% | 8.548%
| Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med
Editable Threshholds for RAIN Colour Scale Indicators | Low > | 50 | > Med > | 100 | >High
Wind
Mean 3pm wind speed (km/h) | 23.3 | 22 | 21.2 | 19.5 | 18.2 | 18.9 | 20.5 | 22 | 22.7 | 23 | 22.6 | 23.1
| Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med
Editable Threshholds for WIND Colour Scale Indicators | Low > | 20 | > Med > | 36 | >High
Tower cranes not able to lift for Wind Gusts > 70kph
Mobile cranes not able to lift for Wind Gusts > 36kph
Wind loads are dependent on crane types,
mobile cranes have a significantly lower permissible
wind speed than tower cranes generally

## Weather Calculation
Forecast Delay Allowances |  |  |  |  | Annual Totals |  | Year | [5 empty] | 1905-07-09
[7 empty] | 2017-01-01 | 2017-02-01 | 2017-03-04 | 2017-04-04 | 2017-05-05 | 2017-06-05 | 2017-07-06 | 2017-08-06 | 2017-09-06 | 2017-10-07 | 2017-11-07 | 2017-12-08
[5 empty] | Ratio:Work/MonthDays |  | 48.39% | 78.57% | 74.19% | 63.33% | 80.65% | 70% | 80.65% | 77.42% | 76.67% | 83.87% | 66.67% | 38.71%
INSTRUCTIONS :
Hot Weather (Average days over 37 degrees celcius) Lose |  |  |  | 40% | 1.1247 |  | 0.3871 | 0.36143 | 0.13355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.16258
Cold Weather (<2 degress C.) Lose |  |  |  | 20% | 1.4218 |  | 0 | 0 | 0 | 0.025333 | 0.1129 | 0.364 | 0.53226 | 0.26323 | 0.10733 | 0.016774 | 0 | 0 | Populate the loss factors for Hot Day and Cold Day delays per month in cells E5 & E6. These rows use data from the Climate TAB to calc how many days per month we lose for extreme Hot or Cold days. These numbers are factored for how many days per month we will be working.
Manual Input : Wind (Assumption) |  |  |  |  | 2 |  | 2017-01-01: 0.5; 2017-10-07: 0.5; 2017-11-07: 0.5; 2017-12-08: 0.5
Manual Input : Client / Authority Delays |  |  |  |  | 0
Manual Input : Subcontractor Delays |  |  |  |  | 0
Manual Input : Industrial (Assumption) |  |  |  |  | 2 |  | 2017-04-04: 0; 2017-06-05: 0.5; 2017-08-06: 0.5; 2017-10-07: 0.5; 2017-12-08: 0.5
Manual Input : Plant Delays |  |  |  |  | 0 | [13 empty] | In cells H7 to S12 manually populate Wind + other potential delays based on Climate stats and other data. The Climate TAB has a graph showing Mean 9am and 3pm wind speeds (for reference). Note - These numbers are NOT factored below to account for WorkHours/Day or WorkDays/Month - so numbers entered here will carry forward to the Red TAB unchanged
Manual Input : Other Delays |  |  |  |  | 0
Monthly Total (Working Days lost per Calendar Month) |  |  |  |  | 6.5465 |  | 0.8871 | 0.36143 | 0.13355 | 0.025333 | 0.1129 | 0.864 | 0.53226 | 0.76323 | 0.10733 | 1.0168 | 0.58 | 1.1626
Percentage Work Days Lost |  |  |  |  | 2.567% |  | 5.914% | 1.643% | 0.5806% | 0.1333% | 0.4516% | 4.114% | 2.129% | 3.18% | 0.4667% | 3.911% | 2.9% | 9.688%
Cumulative Total (Working Days Lost) | [6 empty] | 0.8871 | 1.2485 | 1.3821 | 1.4074 | 1.5203 | 2.3843 | 2.9166 | 3.6798 | 3.7871 | 4.8039 | 5.3839 | 6.5465
Calculation Notes
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[6 empty] | Rain | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med
[6 empty] | Heat | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med
[6 empty] | Cold / Frost | Low | Low | Med | High | High | High | High | High | High | High | Med | High
[6 empty] | Wind | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med
Working Days |  |  |  |  | Totals | [13 empty] | Row 27 auto populates from the Orange TAB and is used as a lookup table in the Red TAB. These rows show number of working days each month. Row 3 shows the %age ratio of WorkDays/DaysperMonth
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Gross Work Days Per Month (ie Cal Days - Hols, RDOs, NWDs etc) |  |  |  |  | 255 |  | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12
Cumulative Gross Work Days per Calendar Year | [6 empty] | 15 | 37 | 60 | 79 | 104 | 125 | 150 | 174 | 197 | 223 | 243 | 255
Rainfall | Direct | Consequential | Total
<1mm | 0% | 0% | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
≥ 1 mm & < 10 mm | 50% | 100% | 150% |  | 33.7978 |  | 1.0887 | 1.3701 | 1.8363 | 2.2444 | 3.9919 | 3.2681 | 4.5363 | 4.529 | 3.7087 | 3.6327 | 2.4375 | 1.154
≥ 10 mm & < 25 mm | 100% | 100% | 200% |  | 9.1096 |  | 0.39919 | 0.53036 | 0.66774 | 0.6175 | 1.0887 | 0.735 | 0.72581 | 0.92903 | 0.9775 | 1.1323 | 0.9 | 0.40645
≥ 25 mm | 100% | 200% | 300% |  | 6.8147 |  | 0.43548 | 1.1786 | 0.44516 | 0.95 | 0.48387 | 0.21 | 0.48387 | 0.23226 | 0.46 | 0.75484 | 0.6 | 0.58065
RAIN EXPOSURE 1 : Bulk + Inground Works |  |  |  |  | 49.722 |  | 1.9234 | 3.079 | 2.9492 | 3.8119 | 5.5645 | 4.2131 | 5.746 | 5.6903 | 5.1462 | 5.5198 | 3.9375 | 2.1411 | Rows 31 to 65 calculate the monthly impact of each Rain Exposure factor
Rainfall | Direct | Consequential | Total
<1mm | 0% | 0% | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
≥ 1 mm & < 10 mm | 50% | 0% | 50% |  | 11.2659 |  | 0.3629 | 0.4567 | 0.6121 | 0.74812 | 1.3306 | 1.0894 | 1.5121 | 1.5097 | 1.2362 | 1.2109 | 0.8125 | 0.38468
≥ 10 mm & < 25 mm | 100% | 30% | 130% |  | 5.9212 |  | 0.25948 | 0.34473 | 0.43403 | 0.40137 | 0.70766 | 0.47775 | 0.47177 | 0.60387 | 0.63538 | 0.73597 | 0.585 | 0.26419
≥ 25 mm | 100% | 50% | 150% |  | 3.4074 |  | 0.21774 | 0.58929 | 0.22258 | 0.475 | 0.24194 | 0.105 | 0.24194 | 0.11613 | 0.23 | 0.37742 | 0.3 | 0.29032
RAIN EXPOSURE 2 : Foundations . |  |  |  |  | 20.5945 |  | 0.84012 | 1.3907 | 1.2687 | 1.6245 | 2.2802 | 1.6721 | 2.2258 | 2.2297 | 2.1016 | 2.3243 | 1.6975 | 0.93919 | These numbers are factored for both WorkHours/Day and WorkDays/Month
Rainfall | Direct | Consequential | Total
<1mm | 0% | 0% | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
≥ 1 mm & < 10 mm | 50% | 0% | 50% |  | 11.2659 |  | 0.3629 | 0.4567 | 0.6121 | 0.74812 | 1.3306 | 1.0894 | 1.5121 | 1.5097 | 1.2362 | 1.2109 | 0.8125 | 0.38468
≥ 10 mm & < 25 mm | 100% | 25% | 125% |  | 5.6935 |  | 0.2495 | 0.33147 | 0.41734 | 0.38594 | 0.68044 | 0.45937 | 0.45363 | 0.58065 | 0.61094 | 0.70766 | 0.5625 | 0.25403
≥ 25 mm | 100% | 50% | 150% |  | 3.4074 |  | 0.21774 | 0.58929 | 0.22258 | 0.475 | 0.24194 | 0.105 | 0.24194 | 0.11613 | 0.23 | 0.37742 | 0.3 | 0.29032
RAIN EXPOSURE 3 : Structure & Envelope . |  |  |  |  | 20.3667 |  | 0.83014 | 1.3775 | 1.252 | 1.6091 | 2.253 | 1.6538 | 2.2077 | 2.2065 | 2.0772 | 2.296 | 1.675 | 0.92903 | and reflect potential work day losses each month.
Rainfall | Direct | Consequential | Total
<1mm | 0% | 0% | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
≥ 1 mm & < 10 mm | 0% | 0% | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
≥ 10 mm & < 25 mm | 50% | 0% | 50% |  | 2.2774 |  | 0.099798 | 0.13259 | 0.16694 | 0.15438 | 0.27218 | 0.18375 | 0.18145 | 0.23226 | 0.24438 | 0.28306 | 0.225 | 0.10161
≥ 25 mm | 50% | 0% | 50% |  | 1.1358 |  | 0.072581 | 0.19643 | 0.074194 | 0.15833 | 0.080645 | 0.035 | 0.080645 | 0.03871 | 0.076667 | 0.12581 | 0.1 | 0.096774
RAIN EXPOSURE 4 : Fitout & Finishes . |  |  |  |  | 3.4132 |  | 0.17238 | 0.32902 | 0.24113 | 0.31271 | 0.35282 | 0.21875 | 0.2621 | 0.27097 | 0.32104 | 0.40887 | 0.325 | 0.19839 | These numbers copy down to Rows 68 to 73
Rainfall | Direct | Consequential | Total
<1mm | 0% | 0% | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
≥ 1 mm & < 10 mm | 0% | 0% | 0% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
≥ 10 mm & < 25 mm | 25% | 0% | 25% |  | 1.1387 |  | 0.049899 | 0.066295 | 0.083468 | 0.077188 | 0.13609 | 0.091875 | 0.090726 | 0.11613 | 0.12219 | 0.14153 | 0.1125 | 0.050806
≥ 25 mm | 75% | 0% | 75% |  | 1.7037 |  | 0.10887 | 0.29464 | 0.11129 | 0.2375 | 0.12097 | 0.0525 | 0.12097 | 0.058065 | 0.115 | 0.18871 | 0.15 | 0.14516
RAIN EXPOSURE 5 : Custom Rain Impacts . |  |  |  |  | 2.8424 |  | 0.15877 | 0.36094 | 0.19476 | 0.31469 | 0.25706 | 0.14437 | 0.21169 | 0.17419 | 0.23719 | 0.33024 | 0.2625 | 0.19597
Weather Analysis Impact Table
|  |  | Annual |  | Rain Exposure |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Rows 68 to 81 are used as a lookup table in the Red TAB
|  |  | 49.722 | 19.5% | 1 |  | 1.9234 | 3.079 | 2.9492 | 3.8119 | 5.5645 | 4.2131 | 5.746 | 5.6903 | 5.1462 | 5.5198 | 3.9375 | 2.1411
|  |  | 20.5945 | 8.076% | 2 |  | 0.84012 | 1.3907 | 1.2687 | 1.6245 | 2.2802 | 1.6721 | 2.2258 | 2.2297 | 2.1016 | 2.3243 | 1.6975 | 0.93919
|  |  | 20.3667 | 7.987% | 3 |  | 0.83014 | 1.3775 | 1.252 | 1.6091 | 2.253 | 1.6538 | 2.2077 | 2.2065 | 2.0772 | 2.296 | 1.675 | 0.92903
|  |  | 3.4132 | 1.338% | 4 |  | 0.17238 | 0.32902 | 0.24113 | 0.31271 | 0.35282 | 0.21875 | 0.2621 | 0.27097 | 0.32104 | 0.40887 | 0.325 | 0.19839
|  |  | 2.8424 | 1.115% | 5 |  | 0.15877 | 0.36094 | 0.19476 | 0.31469 | 0.25706 | 0.14437 | 0.21169 | 0.17419 | 0.23719 | 0.33024 | 0.2625 | 0.19597
|  |  | 1.1247 | 0.441% | Heat |  | 0.3871 | 0.36143 | 0.13355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.16258
|  |  | 1.4218 | 0.5576% | Cold |  | 0 | 0 | 0 | 0.025333 | 0.1129 | 0.364 | 0.53226 | 0.26323 | 0.10733 | 0.016774 | 0 | 0
|  |  | 2 | 0.7843% | Wind |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
|  |  | 0 | 0% | Client |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0% | Subbie |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2 | 0.7843% | IR |  | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5
|  |  | 0 | 0% | Plant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0% | Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
2

## Critical Site Works Summary
PROJECT TITLE | [103 empty] | For Projects >32 month duration click the + sign above and adjust Print settings to view the relevant number of columns. You may also have to move the JH logo, and drag the blue arrow out to the project finish
OVERALL NET TENDER PROGRAMME: DELAY ANALYSIS
Printed : | 2026-10-17 |  | OVERALL NET PROGRAMME - 6d Working Week, Inclusive of Fixed RDO's, Public Holidays & Xmas / Easter Shut Downs
Planner : | Henry Gannt |  | ONSITE MONTH NUMBER |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96
Commence Works on Site - 03-Sep-18 |  |  | Working Days = 905 |  | 2022-03-21
Activity (with Critical Path in RED) |  | W.D | Net Start | Net Finish | bar: 96
[5 empty] | Gross %age Weather Impact | Net %age Weather Impact | [97 empty] | HoursPerDay:Ratio |  | WorkDaysperYear | time axis 2018-08-31 to 2026-08-15
Assumed Date of CONTRACT AWARD |  |  | 2018-05-25 | [100 empty] | Work Hours : | 37.5% | WorkDays | 69.86%
Assumed START ON SITE DATE |  |  | 2018-09-03 | Rain Exposure Rating > |  |  | 2018-09-15: 3; 2018-10-15: 3; 2018-11-15: 1; 2018-12-15: 1; 2019-01-15: 1; 2019-02-15: 1; 2019-03-15: 1; 2019-04-15: 1; 2019-05-15: 1; 2019-06-15: 2; 2019-07-15: 2; 2019-08-15: 2; 2019-09-15: 3; 2019-10-15: 3; 2019-11-15: 3; 2019-12-15: 3; 2020-01-15: 3; 2020-02-15: 3; 2020-03-15: 3; 2020-04-15: 3; 2020-05-15: 3; 2020-06-15: 3; 2020-07-15: 4; 2020-08-15: 4; 2020-09-15: 4; 2020-10-15: 4; 2020-11-15: 4; 2020-12-15: 4; 2021-01-15: 4; 2021-02-15: 4; 2021-03-15: 4; 2021-04-15: 4; 2021-05-15: 4; 2021-06-15: 4; 2021-07-15: 4; 2021-08-15: 4; 2021-09-15: 4 | Total Hours |  | TotalDays
Site Establishment |  | 41.2192 | 2018-09-03 | 2018-10-31 | 13.34% | 15.39% | 2018-09-15: 2.1845; 2018-10-15: 3.3127 | These ratios are used to multiply the Climate
|  |  | x | x
Clear & Grub + Bulk Excavation |  | 139.726 | 2018-11-01 | 2019-05-19 | 19.09% | 23.59% | 2018-11-15: 4.5175; 2018-12-15: 3.3037; 2019-01-15: 2.8105; 2019-02-15: 3.4404; 2019-03-15: 3.0827; 2019-04-15: 3.8372; 2019-05-15: 5.6774 | data to calculate potential delays
|  |  | x | x
Substructure |  | 63.5753 | 2019-05-20 | 2019-08-18 | 13.04% | 14.99% | 2019-06-15: 2.5361; 2019-07-15: 2.7581; 2019-08-15: 2.9929
x
Precast & Steelwork Structure |  | 225.6575 | 2019-08-19 | 2020-07-06 | 9.396% | 10.37% | 2019-09-15: 2.1845; 2019-10-15: 3.3127; 2019-11-15: 2.255; 2019-12-15: 2.0916; 2020-01-15: 1.7172; 2020-02-15: 1.7389; 2020-03-15: 1.3856; 2020-04-15: 1.6344; 2020-05-15: 2.3659; 2020-06-15: 2.5177
|  |  | x | x
Fitout & Finishes |  | 319.274 | 2020-07-07 | 2021-10-06 | 3.826% | 3.979% | 2020-07-15: 0.79435; 2020-08-15: 1.0342; 2020-09-15: 0.42838; 2020-10-15: 1.4256; 2020-11-15: 0.905; 2020-12-15: 1.361; 2021-01-15: 1.0595; 2021-02-15: 0.69045; 2021-03-15: 0.37468; 2021-04-15: 0.33804; 2021-05-15: 0.46573; 2021-06-15: 1.0827; 2021-07-15: 0.79435; 2021-08-15: 1.0342; 2021-09-15: 0.42838
|  |  | x | x
Testing & Commissioning |  | 115.9726 | 2021-10-07 | 2022-03-21 | 3.571% | 3.703% | 2021-10-15: 1.0168; 2021-11-15: 0.58; 2021-12-15: 1.1626; 2022-01-15: 0.8871; 2022-02-15: 0.36143; 2022-03-15: 0.13355
|  |  | x | x
|  |  | x | x
Working Days |  | 905 |  |  | 8.62% | 9.434%
Inclement Weather Risk | time axis 2018-08-31 to 2026-08-15
Rain risk | [6 empty] | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med
Heat risk | [6 empty] | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low | Low | Med | Med | Med | High | High | Med | Med | Low | Low | Low | Low
Cold / Frost risk | [6 empty] | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High | High | High | Med | High | Low | Low | Med | High | High | High | High | High
Wind risk | [6 empty] | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med | Med | Med | Med | Med | Med | Med | Med | Low | Low | Low | Med | Med
Climate Notes | [6 empty] | 2018-08-31: Weather Data from BoM Weather Station 086077 MOORABBIN AIRPORT
Delay Risk Notes
Forecast Delay Allowance in Working Days |  |  | Totals | bar: 2026-08-15
 | time axis 2018-08-31 to 2026-08-15
Wet Weather |  |  | 54.1273 |  |  |  |  | 2.0772 | 2.296 | 3.9375 | 2.1411 | 1.9234 | 3.079 | 2.9492 | 3.8119 | 5.5645 | 1.6721 | 2.2258 | 2.2297 | 2.0772 | 2.296 | 1.675 | 0.92903 | 0.83014 | 1.3775 | 1.252 | 1.6091 | 2.253 | 1.6538 | 0.2621 | 0.27097 | 0.32104 | 0.40887 | 0.325 | 0.19839 | 0.17238 | 0.32902 | 0.24113 | 0.31271 | 0.35282 | 0.21875 | 0.2621 | 0.27097 | 0.32104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hot Weather (Average days over 37 degrees C.) lose |  | 40% | 4.4986 |  |  |  |  | 0 | 0 | 0.08 | 0.16258 | 0.3871 | 0.36143 | 0.13355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.16258 | 0.3871 | 0.36143 | 0.13355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.16258 | 0.3871 | 0.36143 | 0.13355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.16258 | 0.3871 | 0.36143 | 0.13355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cold Weather (<2 degress C.) Lose |  | 20% | 4.3896 |  |  |  |  | 0.10733 | 0.016774 | 0 | 0 | 0 | 0 | 0 | 0.025333 | 0.1129 | 0.364 | 0.53226 | 0.26323 | 0.10733 | 0.016774 | 0 | 0 | 0 | 0 | 0 | 0.025333 | 0.1129 | 0.364 | 0.53226 | 0.26323 | 0.10733 | 0.016774 | 0 | 0 | 0 | 0 | 0 | 0.025333 | 0.1129 | 0.364 | 0.53226 | 0.26323 | 0.10733 | 0.016774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind (Assumption) |  |  | 8 |  |  |  |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Client / Authority |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontractor |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Industrial (Assumption) |  |  | 7 |  |  |  |  | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plant |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total (Working Days lost) |  |  | 78.0155 |  | 8.62% | 9.434% |  | 2.1845 | 3.3127 | 4.5175 | 3.3037 | 2.8105 | 3.4404 | 3.0827 | 3.8372 | 5.6774 | 2.5361 | 2.7581 | 2.9929 | 2.1845 | 3.3127 | 2.255 | 2.0916 | 1.7172 | 1.7389 | 1.3856 | 1.6344 | 2.3659 | 2.5177 | 0.79435 | 1.0342 | 0.42838 | 1.4256 | 0.905 | 1.361 | 1.0595 | 0.69045 | 0.37468 | 0.33804 | 0.46573 | 1.0827 | 0.79435 | 1.0342 | 0.42838 | 1.0168 | 0.58 | 1.1626 | 0.8871 | 0.36143 | 0.13355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Total | [7 empty] | 2.1845 | 5.4973 | 10.0148 | 13.3185 | 16.129 | 19.5694 | 22.6521 | 26.4894 | 32.1668 | 34.7029 | 37.461 | 40.4539 | 42.6384 | 45.9511 | 48.2061 | 50.2977 | 52.015 | 53.7539 | 55.1394 | 56.7738 | 59.1398 | 61.6575 | 62.4519 | 63.486 | 63.9144 | 65.3401 | 66.2451 | 67.606 | 68.6655 | 69.356 | 69.7306 | 70.0687 | 70.5344 | 71.6172 | 72.4115 | 73.4457 | 73.8741 | 74.8909 | 75.4709 | 76.6334 | 77.5205 | 77.882 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155 | 78.0155
Calculation Notes | [6 empty] | 2018-11-15: 78 Delay Days = 8.6% of overall gross duration
Working Days |  |  | Totals | bar: 2026-08-15
 | time axis 2018-08-31 to 2026-08-15
Gross Work Days (ie Cal Days - Hols, RDOs, NWDs etc) |  |  | 905 |  |  |  |  | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24
Cumulative Gross Work Days | [7 empty] | 23 | 49 | 69 | 81 | 96 | 118 | 141 | 160 | 185 | 206 | 231 | 255 | 278 | 304 | 324 | 336 | 351 | 373 | 396 | 415 | 440 | 461 | 486 | 510 | 533 | 559 | 579 | 591 | 606 | 628 | 651 | 670 | 695 | 716 | 741 | 765 | 788 | 814 | 834 | 846 | 861 | 883 | 906 | 925 | 950 | 971 | 996 | 1020 | 1043 | 1069 | 1089 | 1101 | 1116 | 1138 | 1161 | 1180 | 1205 | 1226 | 1251 | 1275 | 1298 | 1324 | 1344 | 1356 | 1371 | 1393 | 1416 | 1435 | 1460 | 1481 | 1506 | 1530 | 1553 | 1579 | 1599 | 1611 | 1626 | 1648 | 1671 | 1690 | 1715 | 1736 | 1761 | 1785 | 1808 | 1834 | 1854 | 1866 | 1881 | 1903 | 1926 | 1945 | 1970 | 1991 | 2016 | 2040
Nett Work Days (ie Gross Work Days - Monthly Delay Allowance) |  |  | 826.9845 |  | 91.38% |  |  | 20.8155 | 22.6873 | 15.4825 | 8.6963 | 12.1895 | 18.5596 | 19.9173 | 15.1628 | 19.3226 | 18.4639 | 22.2419 | 21.0071 | 20.8155 | 22.6873 | 17.745 | 9.9084 | 13.2828 | 20.2611 | 21.6144 | 17.3656 | 22.6341 | 18.4823 | 24.2056 | 22.9658 | 22.5716 | 24.5744 | 19.095 | 10.639 | 13.9405 | 21.3096 | 22.6253 | 18.662 | 24.5343 | 19.9172 | 24.2056 | 22.9658 | 22.5716 | 24.5744 | 19.095 | 10.639 | 13.9405 | 21.3096 | 22.6253 | 18.662 | 24.5343 | 19.9172 | 24.2056 | 22.9658 | 22.5716 | 24.5744 | 19.095 | 10.639 | 13.9405 | 21.3096 | 22.6253 | 18.662 | 24.5343 | 19.9172 | 24.2056 | 22.9658 | 22.5716 | 24.5744 | 19.095 | 10.639 | 13.9405 | 21.3096 | 22.6253 | 18.662 | 24.5343 | 19.9172 | 24.2056 | 22.9658 | 22.5716 | 24.5744 | 19.095 | 10.639 | 13.9405 | 21.3096 | 22.6253 | 18.662 | 24.5343 | 19.9172 | 24.2056 | 22.9658 | 22.5716 | 24.5744 | 19.095 | 10.639 | 13.9405 | 21.3096 | 22.6253 | 18.662 | 24.5343 | 19.9172 | 24.2056 | 22.9658
Cumulative Net Work Days | [7 empty] | 20.8155 | 43.5027 | 58.9852 | 67.6815 | 79.871 | 98.4306 | 118.3479 | 133.5106 | 152.8332 | 171.2971 | 193.539 | 214.5461 | 235.3616 | 258.0489 | 275.7939 | 285.7023 | 298.985 | 319.2461 | 340.8606 | 358.2262 | 380.8602 | 399.3425 | 423.5481 | 446.514 | 469.0856 | 493.6599 | 512.7549 | 523.394 | 537.3345 | 558.644 | 581.2694 | 599.9313 | 624.4656 | 644.3828 | 668.5885 | 691.5543 | 714.1259 | 738.7003 | 757.7953 | 768.4343 | 782.3748 | 803.6844 | 826.3097 | 844.9717 | 869.5059 | 889.4232 | 913.6288 | 936.5946 | 959.1663 | 983.7406 | 1002.8356 | 1013.4747 | 1027.4152 | 1048.7247 | 1071.3501 | 1090.012 | 1114.5463 | 1134.4635 | 1158.6692 | 1181.635 | 1204.2066 | 1228.781 | 1247.876 | 1258.515 | 1272.4555 | 1293.7651 | 1316.3904 | 1335.0524 | 1359.5866 | 1379.5039 | 1403.7095 | 1426.6753 | 1449.247 | 1473.8213 | 1492.9163 | 1503.5553 | 1517.4959 | 1538.8054 | 1561.4308 | 1580.0927 | 1604.627 | 1624.5442 | 1648.7499 | 1671.7157 | 1694.2873 | 1718.8617 | 1737.9567 | 1748.5957 | 1762.5362 | 1783.8458 | 1806.4711 | 1825.1331 | 1849.6673 | 1869.5846 | 1893.7902 | 1916.756
Formulas:
Net Start = +[Net Start, row above]
Net Finish = +[Net Start]+52+6
Net Finish = +[Net Start]+90
Commence Works on Site - 03-Sep-18
Working Days = 905

## Rain+Other Factors
Typical Standard Rain Factors
|  | EXPOSURE 1 CIVIL Bulk Earthworks & Inground Works below -0.75m |  |  |  | EXPOSURE 2 CIVIL Detailed Excavation BUILDING Foundations and Ground Slabs |  |  | EXPOSURE 3 BUILDING Structure & Envelope |  |  | EXPOSURE 4 BUILDING Fitout & Finishes (sheltered) |  |  | EXPOSURE 5 CUSTOM RAIN IMPACTS Customise as necessary
| Daily | Direct | Consequential | Total |  | Direct | Consequential | Total | Direct | Consequential | Total | Direct | Consequential | Total | Direct | Consequential | Total
| Rainfall | Impact | Delay | Impact |  | Impact | Delay | Impact | Impact | Delay | Impact | Impact | Delay | Impact | Impact | Delay | Impact
| <1mm | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| >1mm | 50% | 100% | 150% |  | 50% | 0% | 50% | 50% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
| >10mm | 100% | 100% | 200% |  | 100% | 30% | 130% | 100% | 25% | 125% | 50% | 0% | 50% | 25% | 0% | 25%
| >25mm | 100% | 200% | 300% |  | 100% | 50% | 150% | 100% | 50% | 150% | 50% | 0% | 50% | 75% | 0% | 75%
RAIN SUMMARY TABLE
| Exposure | Total Impacts of Daily Rainfall
| Level | <1mm | >1mm | >10mm | >25mm
| 1 | 0% | 150% | 200% | 300%
| 2 | 0% | 50% | 130% | 150%
| 3 | 0% | 50% | 125% | 150%
| 4 | 0% | 0% | 50% | 50%
Custom | 5 | 0% | 0% | 25% | 75%
Note : The Standard Rain factors above are editable to account for specific ground conditions, or specific project issues. However the reasons for using non-standard factors MUST be discussed and agreed with Bid Leaders or Project Manager and documeted in the Basis of Schedule

## Project Site Calendar
INSTRUCTIONS :
SETCTION A : Typical Annual Non Work Days FOR REFERENCE |  |  |  | TYPICAL CALENDAR YEAR | [13 empty] | Rows 2 to 27 (Section A) shows Typical Non Work Days for various Australian States & Territories. These are for reference. For other regions please refer to Google and local calendars |  | TYPICAL WORK WEEK
|  |  | Source | 2017-01-01 | 2017-02-01 | 2017-03-04 | 2017-04-04 | 2017-05-05 | 2017-06-05 | 2017-07-06 | 2017-08-06 | 2017-09-06 | 2017-10-07 | 2017-11-07 | 2017-12-08 |  |  |  |  | Day | Work Hours
Calendar Days (Feb has 29 days for Leap Years) |  |  |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 365 |  |  |  | Sunday
Typical Annual Public Holidays 7 National Hols: 2@Christmas, 2@Easter, New Year Day, Australia Day + Anzac Day 3 or 4 Annual State Public Holidays + Show Days Check Calendars or Google |  | National |  | 2 |  |  | 3 | [7 empty] | 2 | 7 |  | Rows 29 to 36 (Section B) Populate these cells with the relevant non-work days for the specific project under consideration. Copy and paste from Section A and /or edit as appropriate |  | Monday | 9
|  | ACT |  |  | 1 |  |  |  | 1 |  |  | 1 | 1 |  |  | 4 |  |  |  | Tuesday | 9
|  | NSW | [6 empty] | 1 |  | 1 |  | 1 |  |  | 3 |  |  |  | Wednesday | 9
|  | NT | [5 empty] | 1 | 1 |  | 1 |  |  |  |  | 3 |  | Comments (right click Insert Comment) can also be added to cells in Section B to record specific holidays that have been included |  | Thursday | 9
|  | QLD | [5 empty] | 1 |  |  | 1 |  | 1 |  |  | 3 |  |  |  | Friday | 9
|  | SA |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 3 |  |  |  | Saturday | 9
|  | TAS |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 3
|  | VIC |  |  | 1 |  |  |  | 1 |  |  | 1 |  | 1 |  | 4 |  |  |  | Hours/Week | 54
|  | WA |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 3
HoursPerDay:Ratio
Sundays (typical 52 p.a.) |  |  |  | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 52 |  |  |  | Work Hours : | 37.5%
Non Work Saturdays - depends on site roster |  |  |  | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 52 |  |  |  | Total Hours
RDO's (These are indicative only and depend on the specific type of work and the individual trade union(s) which might be involved in the project). Please Google individual State+Union RDO Calendars
|  | ACT | MBA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 13 |  |  |  | Adjust the Above Table for Working Hours Per Week
|  | NSW | CFMEU | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 13
|  | NT | CFMEU | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 |  |  |  | This Ratio is used in the calculations in the Green TAB
|  | QLD | CFMEU | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13
|  | SA | MBA | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13
|  | TAS | CFMEU | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13
|  | VIC | AWU | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13
|  | WA | MBA | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
Non Working Days (Xmas / Easter Shut Down) |  |  |  | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 12
SECTION B : ADJUST PROJECT WORK DAY CALENDAR HERE (copy/paste + manual input/edit)
Calendar Days (Feb has 29 days for Leap Years) |  |  |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 365
Non Work SUNDAYS |  |  |  | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 52 | 14.25%
Non Work SATURDAYS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Public Holidays (National) |  |  |  | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 1.918% |  |  | Note - Both ratios in orange boxes are used in the calculation of time lost
Public Holidays (State) |  | VIC |  |  | 1 |  |  |  | 1 |  |  | 1 |  | 1 |  | 4 | 1.096%
Non Work RDO's / Rosters |  | VIC | CFMEU | 3 | 1 | 4 | 1 | 2 | 4 | 1 | 2 | 2 |  | 5 | 4 | 29 | 7.945% | For Clarity please note in cells G34:H35 the relevant State and Union RDO Calendar used
Non Work Xmas/Easter |  |  |  | 6 |  | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 9 | 18 | 4.932%
WORKING DAYS |  |  |  | 15 | 22 | 23 | 19 | 25 | 21 | 25 | 24 | 23 | 26 | 20 | 12 | 255 | 69.86% | <---------- | These numbers populate the GREEN TAB row 27
| Ratio Workdays:CalendarDays |  |  | 48.39% | 78.57% | 74.19% | 63.33% | 80.65% | 70% | 80.65% | 77.42% | 76.67% | 83.87% | 66.67% | 38.71% | 69.86%
WorkdaysPerYear:Ratio
1
2
3
4
5

## Logic Review (hidden)
|  | Sample |  | Assumed | Sample |  | Result
| EXAMPLE TO CHECK FORMULAE | Month |  | Impact | WorkDays | Ratio | Calc'd by
|  | Nov |  | Factor | /month | Hrs/Day | IWA Rev4
| Sample BoM Data | 30 |  |  |  |  | Spreadsheet
| Total number of rain days | 12.2 | 40.67%
a) | Mean number of rain days < 1 mm | 3.6 | 12% |  |  |  | AxBxCxD
b) | Mean number of rain days ≥ 1 mm and < 10 mm | 6.5 | 21.67% | 150% | 80% | 32.74% | 2.5537
c) | Mean number of rain days ≥ 10 mm and < 25 mm | 1.8 | 6%
d) | Mean number of days of rain ≥ 25 mm | 0.3 | 1%
For this example :-
In an average November we would get 6.5 days of rain ≥ 1 mm and < 10 mm
but we only work 24 days of the total 30 days in November (80%)
| So on average we would expect to be impacted 80% * 6.5 days | 5.2 | days
| And for each days rain of this intensity on average we lose 1.5 days (150%) i.e. | 7.8 | days
In this example we only work 10 hr weekdays and 5 hrs Saturday
Sundays have already been excluded in line 15
| So correct ratio should be : 55 hours / (6 x 24 hrs) | 38.19%
| And potential losses would be | 2.9792 | days
This calculation assumes any rain which falls outside our work hours
still affects us the same as if it rains the whole work day
Potentially this is a conservative assumption.
Bills Formula
Factor x (RainDaysPerMth/CalDaysPerMth) x (WorkHrs/24) x (WorkDaysPerMonth)
| 1.5 x (6.5 /30) x (55/6*24) x (24) | 2.9792 | days
Check OK
A
B
C
D
THIS TAB TO BE DELETED
BEFORE UPLOAD TO IMS